## Sheet1
Website Work Tracker
Sl No. | Feature | Time (in days) | Start Date | End Date | Status | Remarks
1 | Authentication and Authorization | 4 | 20-01-2022 | 24-01-2022 | Starting Today, 20-01-2022, Thursday.
2 | Index page/ Landing Page | 3 | 22-01-2022 | 24-01-2022
3 | An automated content scroller (to be used globally on multiple pages) | 2 | 25-01-2022 |  |  | End date will be added with inputs from the designer
4 | Payment Gateway system | 6 | 28-01-2022 | 04-02-2022
5 | Static Pages for “Help”, “About Us”, “Contact Info”, etc | 2 | 05-02-2022 | 06-02-2022
6 | Search/Filter functionality | 3 | 06-02-2022 |  |  | End date will be added with inputs from the designer
7 | Database design |  | 20-01-2022 |  |  | This will be a continuing process throughout the project
8 | Other Pages |  | 07-02-2022 | 15-02-2022
Total Time Required: 30 days
Other requirements
UI / UX, front-end developer
Server
Domain
SEO requirements/audit
Loading time, main focus, has to be below 3 sec even when we are at peak traffic
Visitors will be 100000 per day
Sample content to put on website