## Sheet1
Website Development Plan
Sl No. | Feature | Time (in days) | Start Date | End Date | Notes | Status | Comments
1 | Authentication and Authorization | 4 | 20-01-2022 |  | This will involve creation of functionalities like login, registration, session handling, authorization of resources (for example, if a Specific user is allowed to access a certain page or not, etc)
2 | Index page/ Landing Page | 3 |  |  | This is the page that opens when a user comes to the website from an external location (for example a google link). This is also the page where the user first lands on after a login process successfully concludes. Since this page must have more than one version (at least 2 – one version for logged in users and another for anonymous users), the specified amount time would Be necessary to create and deploy it.
3 | An automated content scroller (to be used globally on multiple pages) | 2 |  |  | This scroller will display selected artwork (could be based on popularity or on some other criteria). The list of artworks will come from the DB. The selection criteria can be changed from the Backend (an admin site feature).
4 | Payment Gateway system | 6 |  |  | This will take time as we would need to implement at least 2 parallel payment systems. Specifically, I intend to implement a paypal based system (as a lot of global businesses and individuals use it for their daily needs), and a Stripe based system. The reason behind 2 separate systems is to cater to 2 different types of customers (most individuals in the US and Western Europe have a paypal account, while our domestic individuals have bank accounts supported by Stripe’s payment system). Also, this will Provide some amount of redundancy in the system.
5 | Static Pages for “Help”, “About Us”, “Contact Info”, etc | 2 |  |  | These pages (static pages) will not be static in the real sense, as they would be database fuelled. However, since the content in these page will not be changing very frequently, we will refer them to as static pages. These pages would be created as per some pre-selected template (that should be constant for all such pages). The actual content will come from the database.
6 | Search/Filter functionality | 3 |  |  | This functionality will be made available from multiple pages (all pages except the static pages). We can assume at this point that there will be 4 such pages (during the initial phase), but the number of such pages will increase as we grow. The search/filter functionality will be based on 3 criteria at the start. If you have any other criteria in your mind, please feel free to let me know. I would love to incorporate it in the website. The 3 criteria that I would like to implement at the start are a) Search based or Artist name, b)Search based on Artwork name and c) Search based on Auction name (auction name will include the auction house name too).
7 | Database design |  |  |  | I have already created a very loose database schema (I am calling it ‘loose’ as I will probably drop a few fields from some of the tables when I start working, and I might also add a few new fields in some of the tables). So this would be a task that will continue as we go on working on our site. Thus, I have not given it any specific number of days. This will be an ongoing task, and It will eat up some of the time from each feature mentioned above.
8 | Other Pages | 2022-10-05 |  |  | This feature is basically mapped to all the dynamic pages that we will create for our site. I have assigned 5 to 10 days for this (the time is variable as we might need some new features that are Not forseen at this point in time.)
Total Time Required: 30 days